## Largometraje
GEType | TID | Dependency | Dependents | StartConstrain | EndConstrain | TIL | SS | TaskIcon | WBS | Task | Priority | Status | Resource | ResourceCost | BSD | BED | BD | ESD | EED | ED | WBSPredecessors | WBSSuccessors | Work | Done | PercentageCompleted | ASD | AED | AD | BCS | ECS | ACS | Notes | TColor | TPColor | BLColor | ACColor | Custom 1 | Custom 2 | Custom 3 | Custom 4 | Custom 5 | Custom 6 | Custom 7 | Custom 8 | Custom 9 | Custom 10 | Custom 11 | Custom 12 | Custom 13 | Custom 14 | Custom 15 | Custom 16 | Custom 17 | Custom 18 | Custom 19 | Custom 20 | ShapeInfoE | ShapeInfoB | ShapeInfoA | LC | TimelineStart | [33 empty] | TimelineEnd | LLC
System | System | System | System | System | System | System | 11¦GS11¦RS11 | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | System | Custom 1 | Custom 2 | Custom 3 | Custom 4 | Custom 5 | Custom 6 | Custom 7 | Custom 8 | Custom 9 | Custom 10 | Custom 11 | Custom 12 | Custom 13 | Custom 14 | Custom 15 | Custom 16 | Custom 17 | Custom 18 | Custom 19 | Custom 20 | System | System | System | System
[9 empty] | Castidad y Obediencia | [51 empty] | 45985 | 45986 | 45987 | 45988 | 45989 | 45990 | 45991 | 45992 | 45993 | 45994 | 45995 | 45996 | 45997 | 45998 | 45999 | 46000 | 46001 | 46002 | 46003 | 46004 | 46005 | 46006 | 46007 | 46008 | 46009 | 46010 | 46011 | 46012 | 46013 | 46014 | 46015 | 46016 | 46017 | 46018 | 46019
[9 empty] | Project Lead: Diego Fernando Núñez Durán | [51 empty] | 45985: W48; 45992: W49; 45999: W50; 46006: W51; 46013: W52
[61 empty] | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
GEType | TID | Dependency | Dependents | StartConstrain | EndConstrain |  |  |  | WBS | Task | Priority | Status | Resource | Resource Cost | Baseline Start | Baseline End | Baseline Duration | Start | Finish | Duration | WBS Predecessors | WBS Successors | Work | Done | % Complete | Actual Start | Actual End | Actual Duration | Baseline Cost | Est. Cost | Actual Cost | Notes | Bar Color | % Color | Baseline Color | Actual Color | Custom 1 | Custom 2 | Custom 3 | Custom 4 | Custom 5 | Custom 6 | Custom 7 | Custom 8 | Custom 9 | Custom 10 | Custom 11 | Custom 12 | Custom 13 | Custom 14 | Custom 15 | Custom 16 | Custom 17 | Custom 18 | Custom 19 | Custom 20 | ShapeInfoE | ShapeInfoB | ShapeInfoA |  | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d | l | m | m | j | v | s | d
T | 20 |  |  |  |  | 0 |  | u | 1 | Dirección | LOW | In Progress | Miguel Alnguel Aguilar Lara |  |  |  |  | 2025-11-03 | 2025-12-02 | 28 |  |  |  | 0 | 76% | [31 empty] | S_TE¦20¦859.8¦87.1¦1033.3¦99
T | 1 |  |  |  |  | 1 |  | u | 1.1 | Guión Final | NORMAL | In Progress | Miguel Alnguel Aguilar Lara |  |  |  |  | 2025-11-03 | 2025-11-28 | 20 |  |  |  | 0 | 50% | [31 empty] | S_TE¦1¦859.8¦105.1¦955.3¦117
T | 35 |  |  |  |  | 1 |  | u | 1.2 | Mapas conceptuales: Deseo y conflicto / Tres niveles de conflicto. | NORMAL | Completed | Diego F. Núñez Durán, Miguel Alnguel Aguilar Lara |  |  |  |  | 2025-12-02 | 2025-12-02 | 1 |  |  |  | 100 | 100% | [31 empty] | S_TE¦35¦1015.8¦123.1¦1033.3¦135
T | 36 |  |  |  |  | 1 |  | u | 1.3 | red principal, árbol familiar y red extendida con Los Tigres y Luis. | NORMAL | Completed | Diego F. Núñez Durán, Miguel Alnguel Aguilar Lara |  |  |  |  | 2025-12-02 | 2025-12-02 | 1 |  |  |  | 100 | 100% | [31 empty] | S_TE¦36¦1015.8¦141.1¦1033.3¦153
T | 34 |  |  |  |  | 1 |  | u | 1.4 | Estructura narrativa | NORMAL | In Progress | Diego F. Núñez Durán, Miguel Alnguel Aguilar Lara |  |  |  |  | 2025-12-02 | 2025-12-02 | 1 |  |  |  | 0 | 50% | [31 empty] | S_TE¦34¦1015.8¦159.1¦1033.3¦171
T | 7 |  |  |  |  | 1 |  | u | 1.5 | Asegurar Locación | LOW | In Progress | Miguel Alnguel Aguilar Lara, Diego F. Núñez Durán |  |  |  |  | 2025-11-24 | 2025-11-28 | 5 |  |  |  | 0 | 80% | [31 empty] | S_TE¦7¦859.8¦177.1¦955.3¦189
T | 3 |  |  |  |  | 0 |  | u | 2 | Conseguir un First de Dirección | HIGH | In Progress | Miguel Alnguel Aguilar Lara, Diego F. Núñez Durán |  |  |  |  | 2025-11-21 | 2026-01-09 | 36 |  |  |  | 0 | 30% | [31 empty] | S_TE¦3¦859.8¦195.1¦1540.3¦207
T | 21 |  |  |  |  | 0 |  | u | 3 | Conseguir Second de Fotografía | HIGH | In Progress | Diego F. Núñez Durán, Miguel Alnguel Aguilar Lara, Maximiliano Gallegos |  |  |  |  | 2025-11-24 | 2025-12-18 | 19 |  |  |  | 0 | 30% | [31 empty] | S_TE¦21¦859.8¦213.1¦1345.3¦225
T | 4 |  |  |  |  | 0 |  | u | 4 | Conseguir Sonidista | HIGH | In Progress | Diego F. Núñez Durán |  |  |  |  | 2025-12-01 | 2025-12-05 | 5 |  |  |  | 0 | 86% | [31 empty] | S_TE¦4¦996.3¦231.1¦1091.8¦243
T | 10 |  |  |  |  | 1 |  | u | 4.1 | Hablar con el Sonidista David Montero | NORMAL | In Progress | Diego F. Núñez Durán |  |  |  |  | 2025-12-01 | 2025-12-05 | 5 |  |  |  | 0 | 86% | [6 empty] | que acepte el trato | [24 empty] | S_TE¦10¦996.3¦249.1¦1091.8¦261
T | 14 |  |  |  |  | 0 |  | u | 5 | Storyboarding y Shot Listing | NORMAL | Planned | Miguel Alnguel Aguilar Lara, Gerardo Muñiz |  |  |  |  | 2026-01-02 | 2026-01-09 | 6 |  |  |  | 0 | 0%
T | 30 |  |  |  |  | 0 |  | u | 6 | Conseguir Productor en Linea | LOW | Completed | Diego F. Núñez Durán |  |  |  |  | 2025-11-28 | 2025-11-28 | 1 |  |  |  | 100 | 100% | [6 empty] | Se selecciono a Fito | [24 empty] | S_TE¦30¦937.8¦285.1¦955.3¦297
T | 31 |  |  |  |  | 0 |  | u | 7 | Productor de Negocios y Finanzas | LOW | Completed | Diego F. Núñez Durán |  |  |  |  | 2025-11-28 | 2025-11-28 | 1 |  |  |  | 100 | 100% | [6 empty] | Francisco Garza | [24 empty] | S_TE¦31¦937.8¦303.1¦955.3¦315
T | 12 |  |  |  |  | 0 |  | u | 8 | Carpeta de Producción | NORMAL | In Progress | Diego F. Núñez Durán, Luz Adriana |  |  |  |  | 2025-11-24 | 2025-12-05 | 10 |  |  |  | 0 | 60% | [31 empty] | S_TE¦12¦859.8¦321.1¦1091.8¦333
T | 25 |  |  |  |  | 0 |  | u | 9 | Presupuesto | LOW | In Progress | Diego F. Núñez Durán, Paco Garza |  |  |  |  | 2025-11-25 | 2025-11-25 | 1 |  |  |  | 0 | 50% | [31 empty] | S_TE¦25¦879.3¦339.1¦896.8¦351
T | 33 |  |  |  |  | 0 |  | u | 10 | Checar Inversionistas | NORMAL | In Progress | Paco Garza, Diego F. Núñez Durán |  |  |  |  | 2025-11-28 | 2026-02-16 | 57 |  |  |  | 0 | 19% | [31 empty] | S_TE¦33¦937.8¦357.1¦1540.3¦369
T | 32 |  |  |  |  | 0 |  | u | 11 | Checar con Paco Pagos y administración | NORMAL | Planned | Diego F. Núñez Durán |  |  |  |  | 2025-11-25 | 2026-01-30 | 49 |  |  |  | 0 | 0% | [31 empty] | S_TE¦32¦879.3¦375.1¦1540.3¦387
T | 24 |  |  |  |  | 1 |  | u | 11.1 | Proveedores (catering) | NORMAL | Planned | Diego F. Núñez Durán, Miguel Alnguel Aguilar Lara |  |  |  |  | 2025-11-25 | 2026-01-30 | 49 |  |  |  | 0 | 0% | [31 empty] | S_TE¦24¦879.3¦393.1¦1540.3¦405
T | 2 |  |  |  |  | 0 |  | u | 12 | Casting | HIGH | Planned | Miguel Alnguel Aguilar Lara, Diego F. Núñez Durán |  |  |  |  | 2025-11-21 | 2026-01-09 | 40 |  |  |  | 0 | 0% | [31 empty] | S_TE¦2¦859.8¦411.1¦1540.3¦423
T | 26 |  |  |  |  | 1 |  | u | 12.1 | Selección de Actores | NORMAL | Planned | Diego F. Núñez Durán, Miguel Alnguel Aguilar Lara |  |  |  |  | 2025-11-25 | 2026-01-09 | 34 |  |  |  | 0 | 0% | [31 empty] | S_TE¦26¦879.3¦429.1¦1540.3¦441
T | 9 |  |  |  |  | 1 |  | u | 12.2 | Hablar con Luis | HIGH | Planned | Miguel Alnguel Aguilar Lara |  |  |  |  | 2025-11-21 | 2025-11-28 | 6 |  |  |  | 0 | 0% | [31 empty] | S_TE¦9¦859.8¦447.1¦955.3¦459
T | 11 |  |  |  |  | 0 |  | u | 13 | Contratos y derechos de imagen | NORMAL | Planned | Diego F. Núñez Durán, GRNG |  |  |  |  | 2025-11-24 | 2026-01-09 | 35 |  |  |  | 0 | 0% | [31 empty] | S_TE¦11¦859.8¦465.1¦1540.3¦477
T | 27 |  |  |  |  | 0 |  | u | 14 | Ensayo con Actores | NORMAL | Planned | Miguel Alnguel Aguilar Lara, Gerardo Muñiz, Diego F. Núñez Durán |  |  |  |  | 2026-01-13 | 2026-01-23 | 9 |  |  |  | 0 | 0%
T | 16 |  |  |  |  | 0 |  | u | 15 | Propuesta de Arte | NORMAL | Planned | Fernando Espinoza, Miguel Alnguel Aguilar Lara, Gerardo Muñiz |  |  |  |  | 2025-12-09 | 2025-12-12 | 4 |  |  |  | 0 | 0% | [31 empty] | S_TE¦16¦1152.3¦501.1¦1228.3¦513
T | 13 |  |  |  |  | 0 |  | u | 16 | Porpuesta Visual | NORMAL | Planned | Miguel Alnguel Aguilar Lara, Gerardo Muñiz |  |  |  |  | 2025-12-15 | 2025-12-31 | 13 |  |  |  | 0 | 0% | [6 empty] | Definir el Estilo Visual: Toman decisiones clave sobre: Paleta de Colores: Qué colores dominarán y qué simbolizarán. Tipo de Iluminación: ¿Naturalista o estilizada? ¿Dura o suave? ¿Alto o bajo contraste? Estilo de Cámara: ¿Cámara en mano (dinámica) o trípode (estática)? ¿Movimientos de cámara fluidos o bruscos? | [24 empty] | S_TE¦13¦1269.3¦519.1¦1540.3¦531
T | 8 |  |  |  |  | 0 |  | u | 17 | Pre-Producción | NORMAL | Planned | Diego F. Núñez Durán, Miguel Alnguel Aguilar Lara |  |  |  |  | 2025-11-24 | 2026-02-13 | 60 |  |  |  | 0 | 0% | [31 empty] | S_TE¦8¦859.8¦537.1¦1540.3¦549
T | 17 |  |  |  |  | 0 |  | u | 18 | Fin de Preproducción | NORMAL | Planned | Miguel Alnguel Aguilar Lara, Diego F. Núñez Durán, Fernando Espinoza, Gerardo Muñiz, Luz Adriana |  |  |  |  | 2025-11-24 | 2026-02-16 | 61 |  |  |  | 0 | 0% | [31 empty] | S_TE¦17¦859.8¦555.1¦1540.3¦567
T | 22 |  |  |  |  | 0 |  | u | 19 | Producción | NORMAL | Planned | Miguel Alnguel Aguilar Lara, Diego F. Núñez Durán, Luz Adriana, Maximiliano Gallegos, GRNG, Gerardo Muñiz, Fernando Espinoza |  |  |  |  | 2026-02-16 | 2026-02-27 | 10 |  |  |  | 0 | 0%
T | 23 |  |  |  |  | 0 |  | u | 20 | Post Producción | NORMAL | Planned | Miguel Alnguel Aguilar Lara, Diego F. Núñez Durán |  |  |  |  | 2026-03-10 | 2026-06-26 | 79 |  |  |  | 0 | 0%
T | 28 |  |  |  |  | 1 |  | u | 20.1 | Montaje | NORMAL | Planned | Diego F. Núñez Durán, Miguel Alnguel Aguilar Lara |  |  |  |  | 2026-03-10 | 2026-06-26 | 79 |  |  |  | 0 | 0%
T | 29 |  |  |  |  | 0 |  | u | 21 | Edición Sonora | NORMAL | Planned | Miguel Alnguel Aguilar Lara, Diego F. Núñez Durán |  |  |  |  | 2026-06-01 | 2026-06-30 | 22 |  |  |  | 0 | 0%
Exported from Gantt Excel on 02-dic-25 16:22:00
Castidad y Obediencia
noviembre-2025
diciembre-2025
Propuesta de Arte
Porpuesta Visual
Dirección
Guión Final
Mapas conceptuales:
red principal, árbol
Estructura narrativa
Asegurar Locación
Conseguir un First d
Conseguir Second de
Conseguir Sonidista
Hablar con el Sonidi
Conseguir Productor
Productor de Negocio
Carpeta de Producció
Presupuesto
Checar Inversionista
Checar con Paco Pago
Proveedores (caterin
Casting
Selección de Actores
Hablar con Luis
Contratos y derechos
Pre-Producción
Fin de Preproducción

## RS11 (hidden)
Resource | Cost | Use Org Holidays | Department |  | Workhours Start | Workhours End | WorkdaySun | WorkdayMon | WorkdayTue | WorkdayWed | WorkdayThu | WorkdayFri | WorkdaySat | Holidays
Organization |  | FALSE |  | DO NOT MODIFY THIS SHEET OR INSERT COLUMNS | 9:00 | 18:00 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Miguel Alnguel Aguilar Lara | 0 | TRUE |  |  | 0.375 | 0.75 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Luz Adriana | 0 | TRUE |  |  | 0.375 | 0.75 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Diego F. Núñez Durán | 0 | TRUE |  |  | 0.375 | 0.75 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Fernando Espinoza | 0 | TRUE |  |  | 0.375 | 0.75 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Gerardo Muñiz | 0 | TRUE |  |  | 0.375 | 0.75 | 0 | 1 | 1 | 1 | 1 | 1 | 0
GRNG | 0 | TRUE |  |  | 0.375 | 0.75 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Maximiliano Gallegos |  | TRUE |  |  | 0.375 | 0.75 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Adolfo (fito) | 0 | TRUE |  |  | 0.375 | 0.75 | 0 | 1 | 1 | 1 | 1 | 1 | 0
Paco Garza | 0 | TRUE |  |  | 0.375 | 0.75 | 0 | 1 | 1 | 1 | 1 | 1 | 0

## GS11 (hidden)
GCTYPE | SSN | DateFormat | WeekNumType | EC | CurrencySymbol | BaselineBudget | EstimatedBudget | ActualCosts | TotalACS | ShowOverdueBar | ShowPercBar | ShowPercDataBar | ShowBaselineBar | ShowActualBar | ShowCompleted | ShowInProgress | ShowPlanned | ShowLate | ShowTimelineGrid | HiliteHolidays | HiliteWorkOffDays | HiliteHolidaysPR | HiliteWorkOffDaysPR | ShowTodayLines | ShowDependencyConnector | ShowGrouping | ShowEstBaseBar | CurrentView | WeekStartDay | EnableBarText | BarTextCharacters | BarTextFontSize | BarTextDataColumnName | BarTextIsBold | BarTextIsItalic | BarTextIsUnderline | PercentageEntryMode | PercentageCalculationType | ProjectName | ThemeName | SelectedTheme | EBC | EMC | PBC | PDC | BBC | ABC | OBC | DLC | TLC | TBC | GBC | PRC | HBC | HC | WC | HCPR | WCPR | CR1C | CR12C | CR2C | CR3C | TGB | EBaseC | TPCH | TPCN | TPCL | TSCC | TSCI | TSCP | HCOL | DCOL | WCOL | MCOL | QCOL | HYCOL | YCOL | HWID | DWID | WWID | MWID | QWID | HYWID | YWID | RCCal | PTRC | TSD | TED | GRT | RefreshTimeline | TimelineVisible | CalcBED | CalcAED | PTDS | csYear | ceYear | csDate | ceDate | SavedDate | HideHolidays | HideWorkOffDays | HideNonWorkingHours | VerticalBorders | LockWB | Campaign
ds082 | 11 | DDD DD\-MMM\-YY | ISO | FALSE | $ | 150000 | 100000 |  | 0 | TRUE | TRUE | TRUE | TRUE | TRUE | 1 | 1 | 1 | 1 | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | 0 | 1 | D | 1 | TRUE | 20 | 9 | Task | TRUE | FALSE | FALSE | manual | simple |  | Blue | Excel | [29 empty] | 480 | 34 | 4 | 1 | 1 | 1 | 1 | 3 | 3 | 6 | 8 | 10 | 12 | 15 | TRUE | TRUE | 2025-11-24 | 2025-12-28 | RS11 | TRUE | TRUE | TRUE | TRUE | TRUE | 2000 | 2050 | 2000-01-01 | 2050-01-01 | 2025-11-21 | FALSE | FALSE | FALSE | TRUE | TRUE | Cus
Classic
Excel
Dark
Custom